AT&T CTx CQE

Performance Engineering & Cybersecurity

Project Implementation Plan

Legacy Agentic Pipeline

LLM-Powered Performance Testing Automation

| Document Version | 2.0.0 ¦ March 2026 |
| --- | --- |
| Classification | AT&T Internal ¦ Confidential |
| Prepared By | CTx CQE Performance Engineering Team |
| Status | DRAFT ¦ Pending AI Governance Approval |

# 1. Executive Summary

The Legacy Agentic Pipeline is a 7-phase, LLM-powered performance testing automation system purpose-built for AT&T's CTx Customer Experience Legacy infrastructure. The pipeline replaces a largely manual testing lifecycle with an end-to-end agentic workflow — from Jira story ingestion and test case extraction through automated script generation, execution orchestration, results analysis, and postmortem knowledge capture.

This implementation plan defines the complete scope, architecture, phase-by-phase work breakdown, risk register, resource requirements, and delivery milestones for the production deployment.

## 1.1 Objective & Business Value

| Metric | Current State | Target with v2.0 |
| --- | --- | --- |
| Test cycle setup time | 3–5 days (manual) | < 4 hours (automated) |
| Script authoring time | 2–4 days per test suite | < 2 hours (generated) |
| Env config validation | Manual ¦ error-prone | Automated golden-config check |
| Postmortem capture | Ad-hoc / inconsistent | Snowflake + RAG indexed |
| Human-in-the-loop control | Full manual oversight | HITL gates at each phase |

## 1.2 Guiding Principles

- Human-in-the-loop (HITL) at every phase boundary — agents propose, engineers decide.

- Azure OpenAI GPT-4o / GPT-4o-mini only — no external LLM API calls outside the AT&T Azure tenant.

- Graduated autonomy — the system earns trust incrementally across release milestones.

- RAG-grounded intelligence — all agent decisions are anchored to indexed enterprise knowledge.

- Auditability — every agent reasoning trace, prompt, and decision is persisted and inspectable.

# 2. Architecture Overview

## 2.1 Pipeline Architecture

The pipeline is structured as a sequential 7-phase ReAct agent loop, each phase implemented as a dedicated LangChain agent with access to a curated toolset. Phases execute in order, separated by HITL approval gates delivered through a React-based web dashboard backed by a FastAPI server with WebSocket streaming.

Figure 1 — Legacy Agentic Pipeline: Architecture Overview

Figure 1. Full 7-phase pipeline: UI / Dashboard layer → Pipeline Orchestrator → Phase agents P1–P7 → Integration layer (14 systems). HITL gates enforce human review at every phase boundary.

| # | Phase | Agent | Key Inputs | Key Outputs |
| --- | --- | --- | --- | --- |
| 1 | Story Analysis | StoryAnalyzerAgent | Jira stories, PIDs/E1s, RAG docs (AskATT API), Snowflake baselines | Test cases, SLA targets, risk profiles |
| 2 | Test Planning | TestPlanGeneratorAgent | Test cases, Dynatrace metrics, app configs, Snowflake baselines | Test plan, workload model, scenarios, Jira stories |
| 3 | Env Triage | EnvConfigAgent | YAML reference configs, AKS/AppGW endpoints, Solace SEMP | Golden config baseline, drift report, remediation commands |
| 4 | Script & Data | ScriptGeneratorAgent | Test plan, protocol specs, bulk data requirements | VuGen .c scripts, JMeter .jmx, bulk data provisioned |
| 5 | Execution | ExecutionOrchestratorAgent | Scripts, golden config, SLA targets | Peak/Break/Stability results, anomaly log, Jira defects |
| 6 | Reporting | ResultsAnalyzerAgent | Execution data, Dynatrace/Prometheus metrics, baselines | Word report, SharePoint publish, Jira defects archived |
| 7 | Postmortem | PostmortemAgent | Phase logs, anomalies, operator notes, RAG history | Snowflake archive, lessons indexed to RAG knowledge base |

## 2.2 Technology Stack

| Layer | Component | Details |
| --- | --- | --- |
| Orchestration | LangChain ReAct Agents | Tool-calling loop, max 15 iterations, full reasoning trace |
| LLM — Reasoning | Azure OpenAI GPT-4o | Phases 1, 2, 4, 5, 6, 7 ¦ 8,192 max tokens ¦ temp 0.1 |
| LLM — Extraction | Azure OpenAI GPT-4o-mini | Phase 3 classification, formatting tasks ¦ cost-optimized |
| RAG | Azure AI Search | Pre-indexed MS Graph (SharePoint, ServiceNow, PowerBI) |
| State Persistence | Pydantic v2 + JSON | PipelineState persisted to disk between phases |
| Data Platform | Snowflake | Baselines, execution results, golden configs, postmortem archive |
| API Server | FastAPI + WebSocket | Real-time HITL dashboard, REST pipeline controls |
| Dashboard | React (Babel UMD) | HITL gates, phase status, env config editor, ticket tracking |
| Test Harness | LRE 26.3 + JMeter | VuGen C scripts, JMX test plans, Jenkins trigger |
| Monitoring | Dynatrace + Prometheus + ELK | Real-time anomaly detection during Phase 5 |
| CI/CD | Jenkins (or GitHub Actions) | Scheduled drift checks, harness job triggers, build orchestration |
| Source Control | Git (internal mirror) | Workspace mono-repo with JSX/Python/YAML/SQL artifacts |

## 2.3 Integration Map

The pipeline integrates with 10 distinct external systems. Each integration has an active status as of this document's revision date.

| System | Integration Type | Status | Notes / Blockers |
| --- | --- | --- | --- |
| Jira (iTrack) | REST API v2 | Active — Read-only | Full read; create/update blocked by current permission scope |
| Azure AI Search | Semantic Search API | Active – LevelUp MCP | RAG index pre-populated via MS Graph connectors |
| MS Graph / SharePoint | MSAL client credentials | BLOCKED | Internal MS Graph endpoint not yet exposed; pending Network/IAM |
| Snowflake | snowflake-connector-python | PENDING | DDL complete; all 7-phase tables pending. Cost analysis/budget approval pending. |
| Dynatrace | REST API v2 | Active | APM metrics, service topology, real-time problems |
| Prometheus | PromQL HTTP API | Active | AKS pod metrics, JVM heap, GC pause |
| ELK | Elasticsearch REST | Active | Error log search, timeout pattern detection |
| LoadRunner Enterprise | LRE REST API 26.3 | BLOCKED | REST API upgrade pending LRE 26.3 deployment; timeslot booking manual |
| Jenkins | REST + Build API | Active | Job triggers, JMeter execution, daily drift cron |
| Azure AKS | kubectl / Azure CLI | Active | Read-only deployment/config inspection |
| Azure AKS | Azure AKS deployment | PENDING | Agentic pipeline cloud deployment. Cost analysis/budget approval pending. |

# 3. Phase-by-Phase Work Breakdown

Each phase below lists discrete implementation work items and their current completion status. Status legend: Complete = delivered and passing validation; In Progress = partially implemented; Blocked = external dependency; Pending = not yet started.

Figure 2: Pipeline Code Execution Flowchart  —  _execute_phases() Logic

Figure 2. Code execution flowchart for PipelineOrchestrator._execute_phases(). Shows phase sequencing, HITL gate logic, approval/rejection paths, stop_after handling, and single-phase Web UI override controls.

## 3.1  Phase 1: Story Analysis  (StoryAnalyzerAgent)

Phase Status: Complete

| Work Item | Status |
| --- | --- |
| Jira REST client — multi-story fetch and sprint JQL | Complete |
| Azure AI Search RAG retrieval (semantic + filtered) | Complete |
| Snowflake baseline lookup (transaction p90/p95/TPS) | Complete |
| Dynatrace service discovery and topology mapping | Complete |
| Test case + SLA target extraction (GPT-4o) | Complete |
| Risk level classification (HIGH / MEDIUM / LOW) | Complete |
| Harness recommendation (LRE vs JMeter) logic | Complete |
| User artifacts augmentation (free text, doc blocks, Jira links, file placeholders) | Complete |
| StoryAnalysisOutput Pydantic model + persistence | Complete |
| HITL approval gate + prompt review UI (Phase 1) | Complete |

## 3.2  Phase 2: Test Planning  (TestPlanGeneratorAgent)

Phase Status: Complete

| Work Item | Status |
| --- | --- |
| Workload model generation: TPS, VUser, transaction mix (must sum 100%) | Complete |
| Scenario definition: LOAD, STRESS, ENDURANCE, SPIKE | Complete |
| App config .md reader tool integration | Complete |
| Dynatrace 7-day production metric ingestion for workload calibration | Complete |
| Environment specification and data preparation steps | Complete |
| Entry/exit criteria builder | Complete |
| Risk register generation | Complete |
| Jira story creation for perf test planning artifact | Complete |
| TestPlan Pydantic model + Word document generation (placeholder) | Complete |
| HITL approval gate + prompt review UI (Phase 2) | Complete |

## 3.3  Phase 3: Env Triage  (EnvConfigAgent)

Phase Status: Complete

| Work Item | Status |
| --- | --- |
| Manifest-aware YAML reference store (per-app, multi-lab, multi-release) | Complete |
| AKS deployment config inspection tool (kubectl / Azure CLI) | Complete |
| Azure App Gateway backend pool validation | Complete |
| Solace SEMP queue/VPN config check | Complete |
| HTTP endpoint health probe tool | Complete |
| QC pointer detection and CRITICAL mismatch flagging | Complete |
| Graduated remediation model (ALERT_ONLY / SUGGEST_FIX / AUTO_REMEDIATE) | Complete |
| Golden config snapshot save to Snowflake | Complete |
| Daily drift check via Jenkins cron (06:00 UTC) | Complete |
| Dashboard YAML editor (view, edit, save env reference files) | Complete |
| App catalog CRUD: add, edit, archive applications | Complete |
| HITL approval gate + prompt review UI (Phase 3) | Complete |

## 3.4  Phase 4: Script & Data  (ScriptGeneratorAgent)

Phase Status: Complete

| Work Item | Status |
| --- | --- |
| VuGen C script generator (Action.c, vuser_init.c, vuser_end.c, globals.h) | Complete |
| Correlation rule insertion (web_reg_save_param, regexp patterns) | Complete |
| Parameterization with CSV data files | Complete |
| JMeter .jmx generator (REST/JSON, SOAP/XML, Solace JMS) | Complete |
| Script syntax validation tool | Complete |
| Single-user dry-run execution tool | Complete |
| LRE script upload tool (blocked pending LRE API upgrade) | Blocked |
| Bulk data provisioning: SQL insert, API provisioning, Amdocs data tools | Complete |
| Data integrity check (row counts, dedup, FK validation) | Complete |
| ScriptDataOutput Pydantic model | Complete |
| HITL approval gate + prompt review UI (Phase 4) | Complete |

## 3.5  Phase 5: Execution  (ExecutionOrchestratorAgent)

Phase Status: In Progress

| Work Item | Status |
| --- | --- |
| Pre-flight golden config drift check (Phase 3 reuse) | Complete |
| LRE test run trigger and polling (start / status / results) | Blocked — LRE API |
| Jenkins JMeter trigger and artifact retrieval | Complete |
| Dynatrace real-time monitoring (60s polling loop) | Complete |
| Prometheus PromQL polling (CPU, memory, JVM heap, GC, pod count) | Complete |
| ELK error pattern and timeout log search | Complete |
| Anomaly detection and severity classification | Complete |
| Anomaly routing table (per system / team) | Complete |
| Jira defect creation for CRITICAL/ERROR anomalies | Complete |
| Peak Point identification algorithm | Complete |
| Breakpoint identification algorithm | Complete |
| Stability / Endurance monitoring (4-hour sustained) | Complete |
| SPIKE test with AKS autoscaler tracking | Complete |
| ExecutionOutput Pydantic model | Complete |
| HITL approval gate + prompt review UI (Phase 5) | Complete |

## 3.6  Phase 6: Reporting  (ResultsAnalyzerAgent)

Phase Status: In Progress

| Work Item | Status |
| --- | --- |
| SLA compliance table (p90/p95 per transaction) | Complete |
| Snowflake historical baseline comparison + trend (IMPROVING/STABLE/DEGRADING) | Complete |
| Peak/breakpoint summary and headroom margin calculation | Complete |
| Stability analysis (p90 drift, memory trend, queue depth) | Complete |
| Anomaly timeline compilation | Complete |
| Defect severity classification (BLOCKER/CRITICAL/MAJOR/MINOR) | Complete |
| Word report generator via python-docx | Complete |
| SharePoint upload via MS Graph (blocked — MS Graph not exposed) | Blocked |
| Go / No-Go / Conditional recommendation logic | Complete |
| Snowflake EXECUTION_RESULTS archival (36+ row baseline) | Complete |
| HITL approval gate + prompt review UI (Phase 6) | Complete |

## 3.7  Phase 7: Postmortem  (PostmortemAgent)

Phase Status: Complete

| Work Item | Status |
| --- | --- |
| Issue cataloging by phase and category (environment/data/tooling/process/technical) | Complete |
| Time lost calculation per issue | Complete |
| Lessons learned synthesis (GPT-4o) | Complete |
| Pattern detection via RAG search across prior cycles | Complete |
| Snowflake POSTMORTEM_ENTRIES and LESSONS_LEARNED archival | Complete |
| Azure AI Search RAG indexing of lessons (feedback loop) | Complete |
| Feedback loop verification (re-query after indexing) | Complete |
| PostmortemOutput Pydantic model | Complete |
| HITL approval gate + prompt review UI (Phase 7) | Complete |

## 3.8  Dashboard & Infrastructure

| Work Item | Status |
| --- | --- |
| React HITL Dashboard — 5-page navigation (Home, New Test, Env Config, History, Tickets) | Complete |
| New Test wizard: app selector, story keys, PID/E1 context IDs, schedule | Complete |
| Context Summary generation via /api/context/summary (Jira + RAG + GPT-4o) | Complete |
| Environment Configuration YAML editor (view / edit / save) | Complete |
| App catalog CRUD UI (Add App, Edit App, Delete App) | Complete |
| Test History table with run drill-down and phase output inspector | Complete |
| Tickets/Defects page (Jira iTrack integration, batch open) | Complete |
| Pipeline Log terminal (real-time, color-coded by level) | Complete |
| Agent Reasoning trace viewer (tool calls summary + step-by-step) | Complete |
| Prompt review panel — per-phase prompt editor + context input | Complete |
| FastAPI backend: all REST endpoints + WebSocket streaming | Complete |
| WebSocket broadcast for real-time HITL event streaming | Complete |
| Snowflake DDL — all 14 tables + 4 views | Complete |
| Per-phase .txt prompt files + @lru_cache loader | Complete |
| Jenkins drift check cron pipeline | Complete |
| AI Governance approval submission | Pending |

# 4. Risk Register & Active Blockers

## 4.1 Active Blockers (P0)

The following blockers must be resolved before full production deployment. Each has an identified owner and mitigation path.

| Blocker | Impact | Owner | Mitigation | Target Date |
| --- | --- | --- | --- | --- |
| MS Graph API not internally exposed | Phase 6 SharePoint publish unavailable; report distribution manual | IAM / Network Ops | Manual upload via SharePoint UI in interim; escalate to Network for API gateway exposure | Q2 2026 |
| Jira API — read-only constraints | Cannot auto-create defect tickets from Phase 5/6 agents | Jira Admin (iTrack) | Pre-create defect templates; agents draft Jira payloads for manual submission | Q2 2026 |
| LRE REST API — pending upgrade | Phase 4 script upload and Phase 5 LRE run trigger unavailable | LRE Platform Team | JMeter + Jenkins as primary harness fallback; LRE reserved timeslots booked manually | Q3 2026 |
| AI Governance approval — pending | Pipeline cannot run autonomously in production until approved | AI Governance Board | Full documentation package submitted; interim demo mode with HITL gates active | Q2 2026 |

## 4.2 Risk Register

| # | Risk Description | Likelihood | Impact | Mitigation | Owner |
| --- | --- | --- | --- | --- | --- |
| 1 | LLM hallucination in test case extraction produces invalid SLA targets | Medium | High | GPT-4o @ temp 0.1; structured JSON output schema enforced; HITL review mandatory before Phase 2 | Performance Engineer (HITL) |
| 2 | Azure OpenAI rate limiting under concurrent agent execution | Low | Medium | GPT-4o-mini used for extraction tasks; tenacity retry with exponential backoff; queued execution | Azure Platform Team |
| 3 | Environment config drift between Phase 3 validation and Phase 5 execution | Medium | High | Daily Jenkins drift check at 06:00 UTC; Phase 5 pre-flight re-validates golden config before any run | CSTEM / Phase 3 agent |
| 4 | QC environment pointers missed by automated checks — invalid test results | Low | Critical | CRITICAL mismatch regex on all QC2/QC3/qc-* patterns; test halted on any mismatch | EnvConfigAgent |
| 5 | Snowflake archival failure corrupts baseline data | Low | High | Write validation after each insert; Snowflake FAIL_SAFE and TIME_TRAVEL enabled; daily backup | Data Engineering |
| 6 | Solace MQ queue saturation from ramp-up too fast | Medium | High | Stepped ramp-up enforced (10–20 VUsers/step); queue depth monitored every 60 seconds | Middleware Team |
| 7 | RAG index staleness — agents reference outdated architecture docs | Medium | Medium | RAG index refresh scheduled monthly; postmortem lessons indexed per cycle to supplement | Performance Eng. |
| 8 | HITL approver availability bottleneck between phases | Medium | Medium | Async approval model via web dashboard; email notification on HITL pending; configurable timeout | Pipeline Orchestrator |
| 9 | VuGen script correlation failure for OPUS dynamic values | Low | High | Dry-run validation mandated in Phase 4; correlation syntax validated before LRE upload | ScriptGeneratorAgent |
| 10 | Amdocs proprietary protocol changes break RAG templates | Low | Medium | RAG template versioned; change control notification from CSTEM; quarterly template review | RAG / Amdocs Team |

# 5. Resource Requirements

## 5.1 Human Resources

| Role | Allocation | Phase Involvement | Responsibilities |
| --- | --- | --- | --- |
| Performance Engineer (Lead) | 100% (FTE) | All phases | Pipeline orchestration, HITL approval decisions, prompt tuning, escalation |
| Performance Engineer (2nd) | 50% (0.5 FTE) | Phases 3–6 | Env validation support, execution monitoring, results review |
| CSTEM Coordinator | 20% (0.2 FTE) | Phase 3 | Environment remediation, QC pointer resolution, golden config sign-off |
| Middleware Team Lead | Ad-hoc | Phases 3, 5 | Solace MQ, GDDN, CSI config validation and anomaly resolution |
| DBA (Oracle / Cassandra) | Ad-hoc | Phases 3, 5 | Connection string validation, bulk data schema, query performance |
| Platform Engineering | Ad-hoc | Phases 3, 5 | AKS replica counts, resource limits, pod autoscaler tuning |
| Jira Admin (iTrack) | One-time | Pre-launch | API permission scope review; label and project key alignment |
| AI Governance Reviewer | One-time | Pre-launch | Governance package review, risk assessment sign-off |
| Azure Platform / IAM | One-time + on-call | Pre-launch | MS Graph API gateway exposure, Azure OpenAI quota, MSAL app registration |
| LRE Platform Team | One-time + Q3 | Pre-launch + Q3 | LRE REST API upgrade coordination, timeslot reservation process |

## 5.2 Infrastructure Resources

| Resource | Current Status | Sizing / Spec | Notes |
| --- | --- | --- | --- |
| Azure OpenAI (GPT-4o) | Active | TPM quota: 40K+ | Shared tenant; confirm quota headroom for concurrent phase runs |
| Azure OpenAI (GPT-4o-mini) | Active | TPM quota: 80K+ | Phase 3 and formatting workloads; cost-optimized |
| Azure AI Search Index | Active | enterprise-knowledge index | Monthly refresh cycle required; semantic config deployed |
| Snowflake Warehouse (PERF_WH) | Active | Medium ¦ auto-suspend 5m | PERF_TESTING DB with all DDL applied; PERF_ENGINEER role configured |
| AKS Cluster (PERF) | Active | aks-perf-cluster | Read-only kubectl access confirmed; Phase 3 inspection only |
| Jenkins Server | Active | jenkins.internal.att.com | Drift check cron job deployed; JMeter job template configured |
| LoadRunner Enterprise 26.3 | Active (manual) | lre.internal.att.com | REST API not available; timeslot booking manual until Q3 2026 |
| Python Runtime | Active | >= 3.11 ¦ .venv | All 50-file codebase installed; pyproject.toml dependencies pinned |
| Node.js (dashboard build) | Active | Node 18+ ¦ npm | regen_dashboard_html.js + Babel UMD pipeline |
| Git Repository (internal) | Active | Mono-repo ¦ main branch | perf-test-agent/ + dashboard JSX/HTML at workspace root |

# 6. Milestones & Timeline

## 6.1 Release Roadmap

The pipeline follows a four-milestone release cadence aligned to AT&T sprint cycles. Each milestone represents a tested, HITL-approved increment, with Milestone 4 constituting full production readiness.

| MS | Name | Target | Scope | Exit Criteria |
| --- | --- | --- | --- | --- |
| M1 | Demo & Governance Package | Q2 2026 — Apr | All 7 phases in simulation mode; HITL dashboard fully operational; AI Governance submission complete | Governance package submitted; demo walkthrough with stakeholders complete; simulation passes end-to-end |
| M2 | Live Backend — Phases 1–3 | Q2 2026 — May | Phase 1 (Jira + RAG), Phase 2 (planning), Phase 3 (env validation) connected to live systems; MS Graph blocker resolved | 3 consecutive live runs complete; golden config established on PERF; HITL approval latency < 30 min |
| M3 | Live Backend — Phases 4–6 | Q3 2026 — Jul | Script generation (JMeter/VuGen), execution (Jenkins/LRE), reporting (Snowflake + Word); LRE API unblocked | Full Phase 1–6 live run delivered; peak/break/stability results captured; Word report published to SharePoint |
| M4 | Full Production — Phase 7 + RAG Loop | Q3 2026 — Sep | Postmortem + RAG feedback loop; all 14 integrations live; AI Governance approval granted; team onboarded | AI Governance approved; 5 consecutive sprint cycles executed autonomously; lessons RAG-indexed each cycle |

## 6.2 Sprint-Level Task Schedule

| Sprint / Week | Milestone | Key Deliverables | Dependencies |
| --- | --- | --- | --- |
| Sprint 26.3 Apr Wk 1–2 | M1 | Finalize AI Governance package; stakeholder demo of HITL dashboard (simulation); complete Phase 1–7 documentation | Governance template from AI CoE |
| Sprint 26.3 Apr Wk 3–4 | M1 | AI Governance submission; demo dry-run with leadership; resolve any package feedback | AI Governance Board availability |
| Sprint 26.4 May Wk 1–2 | M2 | MS Graph API gateway exposure (IAM); MSAL app registration; test Phase 6 SharePoint upload | Network Ops / IAM ticket |
| Sprint 26.4 May Wk 3–4 | M2 | Phase 1 live run (real Jira stories); Phase 2 test plan generation; Phase 3 golden config on PERF | Jira API permissions; Azure Search quota |
| Sprint 26.5 Jun Wk 1–2 | M2 | Phase 1–3 end-to-end live run x2; HITL timing benchmarks; prompt tuning from live results | CSTEM env readiness |
| Sprint 26.5 Jun Wk 3–4 | M2→M3 | Phase 4 JMeter script generation live; bulk data provisioning (TLG API, Oracle SQL) | Data provisioning scripts |
| Sprint 26.6 Jul Wk 1–2 | M3 | Phase 5 execution via Jenkins/JMeter; Dynatrace + Prometheus live monitoring loop | LRE timeslot (manual) or Jenkins JMeter |
| Sprint 26.6 Jul Wk 3–4 | M3 | Phase 6 live results analysis; Word report + Snowflake archival; Phase 1–6 end-to-end run | SharePoint unblocked (M2 dep.) |
| Sprint 26.7 Aug Wk 1–2 | M3→M4 | LRE REST API upgrade (if available); Phase 4 LRE script upload automation | LRE Platform Team delivery |
| Sprint 26.7 Aug Wk 3–4 | M4 | Phase 7 postmortem live; RAG lesson indexing; feedback loop verification | Azure AI Search indexer refresh |
| Sprint 26.8 Sep Wk 1–2 | M4 | AI Governance approval follow-through; team onboarding and runbook finalization | Governance Board approval |
| Sprint 26.8 Sep Wk 3–4 | M4 | Production go-live; Sprint 26.8 test cycle as first autonomous run; retrospective | All M1–M3 exit criteria met |

## 6.3 Completion Summary

| Component | Work Items | Complete | Completion % |
| --- | --- | --- | --- |
| Phase 1 — Story Analysis | 9 | 9 | 100% |
| Phase 2 — Test Planning | 10 | 10 | 100% |
| Phase 3 — Env Triage | 12 | 12 | 100% |
| Phase 4 — Script & Data | 11 | 10 | 91% (LRE upload blocked) |
| Phase 5 — Execution | 15 | 13 | 87% (LRE trigger blocked) |
| Phase 6 — Reporting | 11 | 10 | 91% (SharePoint blocked) |
| Phase 7 — Postmortem | 9 | 9 | 100% |
| Dashboard & Infrastructure | 16 | 14 | 88% (Governance pending) |
| Integration Connections (14 total) | 14 | 10 | 71% (4 blocked) |

# 7. Document Control

This document is maintained by the CTx CQE Performance Engineering & Cybersecurity team. Updates are published to the SharePoint CTxCQE site upon each milestone completion.

| Version | Date | Author | Change Summary |
| --- | --- | --- | --- |
| 2.0.0 | March 2026 | CTx CQE Performance Engineering | Initial v2.0 implementation plan — full pipeline scope |
| 2.0.1 | (next revision) | — | Update following AI Governance approval and M1 demo |